## Project Planner
Cleanbot - Group Project CO600
| We are using "Gantt Project Planner" template that has been provided by Microsof to track our project by unique activities. |  |  |  |  | Period Highlight: | 1 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) |  |  |  | % Complete (beyond plan)
| ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 Final Week
15th October(Week 4)
| First meeting with DJB. | 4 | 1 | 4 | 1 | 100%
| Split tasks for Week 4 between group members | 4 | 1 | 4 | 1 | 100%
| Start learn Alexa API. | 4 | 3 | 4 | 4 | 75%
| Discuss about prototype of the project | 4 | 1 | 4 | 1 | 100%
| Start Documentation | 4 | 1 | 4 | 1 | 100%
| Create a shared calender (to see group member's deadlines) | 4 | 1 | 4 | 1 | 100%
| Daily scrums | 4 | 1 | 4 | 1 | 100%
| Create Project Planner | 4 | 1 | 4 | 1 | 100%
| Create Facebook group chat | 4 | 1 | 4 | 1 | 100%
| Create Gantt Chart | 4 | 1 | 4 | 1 | 100%
| Create Templates for documentation | 4 | 1 | 4 | 1 | 100%
| Created 2 weekly meeting (Monday and Friday) | 4 | 1 | 4 | 1 | 100%
| Also, agreed on additional meetings if it's necessary | 4 | 1 | 4 | 1 | 100%
| Discuss about what we are going to do next week (add follow-up actions) | 4 | 1 | 4 | 1 | 100%
22th October(Week 5)
| Start first prototyping (lego digital designer) | 5 | 1 | 5 | 1 | 100%
| Stand-up meeting (what we accomplish? what we struggling with? what we currently working on? what we plan to finish today? | 5 | 1 | 5 | 1 | 100%
| Split weekly task between group members | 5 | 1 | 5 | 1 | 100%
| Quick discussion sections right after meeting with DJ Barnes | 5 | 1 | 5 | 1 | 100%
| Group conversations on "Slack", answered group members' questions and decide on next week meeting's topis | 5 | 1 | 5 | 1 | 100%
| Start designing Python program | 5 | 2 | 5 | 2 | 100%
| Review of EV3 | 5 | 1 | 5 | 1 | 100%
| Building basic skills with Alexa | 5 | 2 | 5 | 4 | 60%
| Learn node.js by using CodeAcademy | 5 | 2 | 5 | 2 | 100%
| Learn Alexa Skills by using CodeAcademy | 5 | 2 | 5 | 2 | 100%
| Daily scrums | 5 | 1 | 5 | 1 | 100%
| Read blogs about Alexa skills | 5 | 1 | 5 | 1 | 100%
| Start learning node.js | 5 | 1 | 5 | 1 | 100%
| Create flow diagram for project | 5 | 1 | 5 | 1 | 100%
| Start prototyping with actual hardware | 5 | 1 | 5 | 1 | 100%
| Search libraries that we can use for our project | 5 | 1 | 5 | 1 | 100%
| Searching about image recognition | 5 | 1 | 5 | 1 | 100%
| Update the Gantt Chart | 5 | 1 | 5 | 1 | 100%
| Start looking lambda function | 5 | 1 | 5 | 2 | 100%
| Discuss about what we are going to do next week (add follow-up actions) | 5 | 1 | 5 | 1 | 100%
29th October(Project Week)
| Create gitHub for Cleanbot | 6 | 1 | 6 | 1 | 100%
| Split weekly task between group members | 6 | 1 | 6 | 1 | 100%
| Stand-up meeting (what we accomplish? what we struggling with? what we currently working on? what we plan to finish today? | 6 | 1 | 6 | 1 | 100%
| Quick discussion sections right after meeting with DJ Barnes | 6 | 1 | 6 | 1 | 100%
| Create software and acceptance test planning | 6 | 1 | 6 | 1 | 100%
| Daily scrums | 6 | 1 | 6 | 1 | 100%
| Pair programing | 6 | 1 | 6 | 1 | 100%
| Practicing more on node.js | 6 | 1 | 6 | 1 | 100%
| Look over what we have done so far | 6 | 1 | 6 | 1 | 100%
| Develop minimum viable project(MVP) | 6 | 1 | 6 | 1 | 100%
| Create python code to control the EV3 motors on prototype | 6 | 1 | 6 | 1 | 100%
| Update the Gantt Chart | 6 | 1 | 6 | 1 | 100%
| Create AWS(Amazon Web Servers) account | 6 | 1 | 6 | 1 | 100%
| Use flask-ask(Amazon Skill Kit) | 6 | 1 | 6 | 3 | 75%
| Develop second prototyping | 6 | 1 | 6 | 1 | 100%
| Discuss about what we are going to do next week (add follow-up actions) | 6 | 1 | 6 | 1 | 100%
5th November(Week 7)
| New ideas generation (how the device will collect small objects) | 7 | 3 | 7 | 3 | 50%
| Split weekly task between group members | 7 | 1 | 7 | 1 | 100%
| Stand-up meeting (what we accomplish? what we struggling with? what we currently working on? what we plan to finish today? | 7 | 1 | 7 | 1 | 100%
| Quick discussion sections right after meeting with DJ Barnes | 7 | 1 | 7 | 1 | 100%
| Develop ideas how the device will collect small object | 7 | 3 | 7 | 3 | 50%
| Discuss what sensor we are going to use | 7 | 1 | 7 | 1 | 100%
| Discuss next iteration of the prototype | 7 | 1 | 7 | 1 | 100%
| Create User Stoires | 7 | 1 | 7 | 1 | 100%
| Create User Requirements | 7 | 1 | 7 | 1 | 100%
| Daily scrums | 7 | 1 | 7 | 1 | 100%
| Create a software skeleton plan | 7 | 1 | 7 | 1 | 100%
| Update the Gantt Chart | 7 | 1 | 7 | 1 | 100%
| Update software and acceptance testing planning | 7 | 1 | 7 | 1 | 100%
| Group conversations on "Slack", answered group members' questions and decide on next week meeting's topis | 7 | 1 | 7 | 1 | 100%
| Order MicroSD card from Amazon | 7 | 1 | 7 | 1 | 100%
| Discuss about what we are going to do next week (add follow-up actions) | 7 | 1 | 7 | 1 | 100%
12th November(Week 8)
| Start making "User Guide" | 8 | 1 | 8 | 1 | 100%
| Split weekly task between group members | 8 | 1 | 8 | 1 | 100%
| Stand-up meeting (what we accomplish? what we struggling with? what we currently working on? what we plan to finish today? | 8 | 1 | 8 | 1 | 100%
| Quick discussion sections right after meeting with DJ Barnes | 8 | 1 | 8 | 1 | 100%
| Struggling Connecting Alexa Skills to Web Socket and Web Socket to EV3 pbrick | 8 | 1 | 8 | 1 | 100%
| Find decent resources for our project | 8 | 1 | 8 | 1 | 100%
| Use Lego Digital Designer (LDD) for third prototype | 8 | 1 | 8 | 1 | 100%
| Research about how to connect two pbrick to each other | 8 | 1 | 8 | 1 | 100%
| Daily scrums | 8 | 1 | 8 | 1 | 100%
| Start Project Planning | 8 | 1 | 8 | 1 | 100%
| Create Ngrok account (for connect Cleanbot to Alexa) | 8 | 1 | 8 | 1 | 100%
| Facing some problems with SSL certificate | 8 | 1 | 8 | 2 | 30%
| Update the Gantt Chart | 8 | 1 | 8 | 1 | 100%
| Develop basic skill for Alexa (Move Forward) | 8 | 1 | 8 | 1 | 100%
| Add EV3 code and Web Server to gitHub | 8 | 1 | 8 | 1 | 100%
| Decide to use library called flask-ask and had some troubles to install because it only installs with one of the pip | 8 | 1 | 8 | 1 | 100%
| Create working branch for first skill | 8 | 1 | 8 | 1 | 100%
| Continue on User Stories and Requirements Document | 8 | 1 | 8 | 1 | 100%
| Start creating Bug Report document (If a bug appears while we testing the Cleanbot, we will keep record it and try to solve the problem | 8 | 1 | 8 | 1 | 100%
| Discuss about what we are going to do next week (add follow-up actions) | 8 | 1 | 8 | 1 | 100%
| Create GitHub documentation (we will update it in future) | 8 | 1 | 8 | 1 | 100%
19th November(Week 9)
| Split weekly task between group members | 9 | 1 | 9 | 1 | 100%
| Stand-up meeting (what we accomplish? what we struggling with? what we currently working on? what we plan to finish today? | 9 | 1 | 9 | 1 | 100%
| Do more online research about project | 9 | 1 | 9 | 1 | 100%
26th November(Week 10)
3rd December(Week 11)
10th December(Week 12) - last week of first term
End of Project